## W & G
JIGAWA STATE SMALL TOWNS WATER SUPLLY AND SANITATION AGENCY (STOWA)
ANNUAL PROCUREMENT PLAN
PROCUREMENT PLAN FOR WORKS AND GOODS CONTRACTS
| MINISTRY/ AGENCY: | STOWA
| BUDGET YEAR: | 2024
| PROJECT PARTICULARS |  |  |  | BASIC DATA |  |  | PROJECT PREPARATION |  |  |  | BIDDING PERIOD |  | BID EVALUATION & AWARD |  |  | CONTRACT MANAGEMENT & ADMINISTRATION |  |  |  | ANY OTHER REMARKS
| Project Description | Economic Code | Package No./File No. | Lot No. | Revised Threshold/ Budgeted Amount (Naira) | Estimated Amount in Naira | Procurement Method | Preparation & Submission of documents by MDAs | Post Review/ Vetting | Advert for Pre - Qualification | Pre-Qualification | Bid Invitation | Bid receipt and opening | Bid Evaluation& Report | Consideration of TEC Recommendation | Due Process Certificate of No Objection | Contract Approval & Offer | Contract Signing | Delivery/handover and acceptance | Final Payment
Date: Plan | i. Rehabilitation of existing small towns water supply schemes | 020404/02 | STOWA/2024/CP/REHAB./1 | NA | 300million | 100 million | Selective method | 19/01/2024-26/01/2024 | 29/01/2024-5/02/2024 | NA | 5/02/2024-12/2/2024 | 12/2/2024-15/2/2024 | 15/2/2024-22/2/2024 | 22/2/2024-26/02/2024 | 26/02/2024-28/02/2024 | 28/02/2024-04/03/2024 | 04/3/2024-11/3/2024 | 11/3/2024-18/3/2024 | 18/3/2024-29/03/2024 | 29/03/2024-05/4/2024 | First Quarter
Date: Actual
Cost :Plan | [18 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | ii. Construction of 30No. New conventional solar water schemes across the 7 zones | 020408/02 | STOWA/2024/CP/2 | NA | 300 million | 150 million | sellective method | 19/01/2024-26/01/2024 | 29/01/2024-5/02/2024 | NA | 5/02/2024-12/2/2024 | 12/2/2024-15/2/2024 | 15/2/2024-22/2/2024 | 22/2/2024-26/02/2024 | 26/02/2024-28/02/2024 | 28/02/2024-04/03/2024 | 04/3/2024-11/3/2024 | 11/3/2024-18/3/2024 | 18/3/2024-29/03/2024 | 29/03/2024-05/4/2024 | First Quarter
Date: Actual
Cost :Plan | [7 empty] | 20000 |  |  | 30000 |  |  | 120000 | 30000 |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | iii.Conversion and upgrading of 40No. motorized water supply scheme to solar powered water supply schemes | 020408/02 | STOWA/2024/PROJ/CP/3 | NA | 400 Million | 150 Million | selective competitive Method | 19/01/2024-26/01/2024 | 29/01/2024-5/02/2024 | NA | 5/02/2024-12/2/2024 | 12/2/2024-15/2/2024 | 15/2/2024-22/2/2024 | 22/2/2024-26/02/2024 | 26/02/2024-28/02/2024 | 28/02/2024-04/03/2024 | 04/3/2024-11/3/2024 | 11/3/2024-18/3/2024 | 18/3/2024-29/03/2024 | 29/03/2024-05/4/2024 | first Quarter
Date: Actual
Cost :Plan | [7 empty] | 70000 |  |  | 50000 |  |  | 120000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | iv. Reinforcement/improvement of reticulation for 5km in 5No. Small towns | 020406/02 | STOWA/2024/CP/4 | NA | 30million | 10million | Nominative Method | 19/01/2024-26/01/2024 | 29/01/2024-5/02/2024 | NA | 5/02/2024-12/2/2024 | 12/2/2024-15/2/2024 | 15/2/2024-22/2/2024 | 22/2/2024-26/02/2024 | 26/02/2024-28/02/2024 | 28/02/2024-04/03/2024 | 04/3/2024-11/3/2024 | 11/3/2024-18/3/2024 | 18/3/2024-29/03/2024 | 29/03/2024-05/4/2024 | First Quarter
Date: Actual
Cost: Plan | [7 empty] | 50000 |  |  | 50000 | [7 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | v. Commencement of 2024 constituency projects | 020408/02 | STOWA/2024/CP/5 | NA | 211.9million | 211.9 million | Open competitive Method | 19/01/2024-26/01/2024 | 29/01/2024-5/02/2024 | NA | 5/02/2024-18/03/2024 | 5/02/2024-18/03/2024 | 5/02/2024-18/03/2024 | 18/03/2024-25/03/2024 | 25/03/2024-28/03/2024 | 28/03/2024-01/04/2024 | 01/04/2024-08/4/2024 | 08/04/2024-12/04/2024 | 12/04/2024-16/04/2024 | 16/04/2024-19/4/2024 | First Quarter
Date: Actual
Cost: Plan | [7 empty] | 50000 |  |  | 50000 | [7 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | vi. Completion of 2022/2023 constituency project | 020408/02 | STOWA/2024/CP/6 | NA | 216 million | 100 million | Open competitive Method | Ongoing project | ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | 10/01/2024-29/03/2024 | 10//01/2024-05/04/2024 | First Quarter
Date: Actual
Cost: Plan | [7 empty] | Ongoing project |  |  | ongoing project |  | ongoing project | [5 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | vii. Establishhment of WCA in community and several follow up visit to 200 communities for monitoring of activities | 020411/02 | STOWA/2024/WCA/7 | NA | 10million | 10million | Direct method | 19/01/2024-26/01/2024 | Direct | NA | Direct | Direct | Direct | Direct | Direct | Direct | 04/3/2024-11/3/2024 | Direct | Direct | 29/03/2024-05/4/2024 | First Quarter
Date: Actual
Cost :Plan | [7 empty] | 60000 |  |  | 80000 | [7 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | vii. Procurement of 1No. Toyota Hillux project vehicles and Toyota corolla(2014 model) | 020411/02 | STOWA/2024/PRCMNT/8 | NA | 60million | 60million | Sellective method | 19/01/2024-26/01/2024 | 29/01/2024-5/02/2024 | NA | 5/02/2024-12/2/2024 | 12/2/2024-15/2/2024 | 15/2/2024-22/2/2024 | 22/2/2024-26/02/2024 | 26/02/2024-28/02/2024 | Direct | 04/3/2024-11/3/2024 | Direct | Direct | 29/03/2024-05/4/2024 | First Quarter
Date: Actual
Cost :Plan | [7 empty] | 60000 |  |  | 80000 | [7 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | ix. Rehabilitation of existing small towns water supply schemes | 020404/02 | STOWA/2024/CP/9 | NA | 300million | 150 million | Sellective Method | 3/4/2024-5/4/2024 | 8/4/2023-12/4/2024 | NA | 12/04/2023-19/4/2024 | 19/4/2024-24/4/2024 | 25/4/2024-30/4/2024 | 1/5/2024-6/5/2024 | 6/5/2024-15/5/2024 | 15/5/2024-22/5/2024 | 22/5/2024-29/5/2024 | 29/6/2024-5/6/2024 | 5/6/2024-26/6/2024 | 26/6/2024-3/7/2024 | second -quarter
Date: Actual
Cost: Plan | [7 empty] | 50000 |  |  | 50000 | [7 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | x. Upgrading and Conversion of 40No. motorized water supply scheme to solar powered water supply schemes | 020408/02 | STOWA/2024/CP/10 | NA | 400 million | 150 millioin | Sellective Method | 3/4/2024-5/4/2024 | 8/4/2023-12/4/2024 | NA | 12/04/2023-19/4/2024 | 19/4/2024-24/4/2024 | 25/4/2024-30/4/2024 | 1/5/2024-6/5/2024 | 6/5/2024-15/5/2024 | 15/5/2024-22/5/2024 | 22/5/2024-29/5/2024 | 29/6/2024-5/6/2024 | 5/6/2024-26/6/2024 | 26/6/2024-3/7/2024 | second quarter
Date: Actual
Cost :Plan | [7 empty] | 50000 |  |  | 40000 | [7 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xi. Commencement of 2024 constituency projects | 020404/02 | STOWA/2024/CP/11 | NA | 211.9million | 211.9million | Open competitive Method | 3/4/2024-5/4/2024 | 8/4/2023-12/4/2024 | NA | 12/04/2023-19/4/2024 | 19/4/2024-24/4/2024 | 25/4/2024-30/4/2024 | 1/5/2024-6/5/2024 | 6/5/2024-15/5/2024 | 15/5/2024-22/5/2024 | 22/5/2024-29/5/2024 | 29/6/2024-5/6/2024 | 5/6/2024-26/6/2024 | 26/6/2024-3/7/2024 | second quarter
Date: Actual
Cost :Plan | [7 empty] | 50000 |  |  | 60000 | 700000 | [6 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xii. Construction of 30No. New solar powered water supply schemes across the 7 zones | 020408/02 | STOWA/2024/CP/12 | NA | 300million | 100 million | sellective method | 3/4/2024-5/4/2024 | 8/4/2023-12/4/2024 | NA | 12/04/2023-19/4/2024 | 19/4/2024-24/4/2024 | 25/4/2024-30/4/2024 | 1/5/2024-6/5/2024 | 6/5/2024-15/5/2024 | 15/5/2024-22/5/2024 | 22/5/2024-29/5/2024 | 29/6/2024-5/6/2024 | 5/6/2024-26/6/2024 | 26/6/2024-3/7/2024 | second quarter
Date: Actual
Cost :Plan | [7 empty] | 20000 |  |  | 30000 |  |  | 120000 | 30000 |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xiii.Completion of 2022/2023 constituency projects | 020408/02 | STOWA/2024/CP/13 | NA | 216 Million | 50 Million | Ongoing project | Ongoing project | ongoing project | NA | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | 5/6/2024-26/6/2024 | 26/6/2024-3/7/2024 | second quarter
Date: Actual
Cost :Plan | [7 empty] | 70000 |  |  | 50000 |  |  | 120000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xiv. Reinforcement/improvement of reticulation for 5 kilometer in 5 small towns | 020406/02 | STOWA/2024/CP/14 | NA | 30 million | 10 million | Nominative Method | 3/4/2024-5/4/2024 | 8/4/2023-12/4/2024 | NA | 12/04/2023-19/4/2024 | 19/4/2024-24/4/2024 | 25/4/2024-30/4/2024 | 1/5/2024-6/5/2024 | 6/5/2024-15/5/2024 | 15/5/2024-22/5/2024 | 22/5/2024-29/5/2024 | 29/6/2024-5/6/2024 | 5/6/2024-26/6/2024 | 26/6/2024-3/7/2024 | second -quarter
Date: Actual
Cost: Plan | [7 empty] | Ongoing project |  |  | ongoing project |  | ongoing project | [5 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xv. Drilling of 5No. Additional complete boreholes with accessories | 020406/02 | STOWA/2024/CP/14 | NA | 10million | 5million | Nominative Method | 3/4/2024-5/4/2024 | 8/4/2023-12/4/2024 | NA | 12/04/2023-19/4/2024 | 19/4/2024-24/4/2024 | 25/4/2024-30/4/2024 | 1/5/2024-6/5/2024 | 6/5/2024-15/5/2024 | 15/5/2024-22/5/2024 | 22/5/2024-29/5/2024 | 29/6/2024-5/6/2024 | 5/6/2024-26/6/2024 | 26/6/2024-3/7/2024 | Second-Quarter
Date: Actual
Cost :Plan | [7 empty] | 30000 |  |  | 50000 | [7 empty] | 30000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xvi. Establishhment of WCA in community and several follow up visit to 200 communities for monitoring of activities | 020411/02 | STOWA/2024/WCA/15 | NA | 10million | 10million | Direct method | 3/4/2024-5/4/2024 | 8/4/2023-12/4/2024 | NA | Direct | Direct | Direct | Direct | Direct | Direct | Direct | Direct | Direct | 26/6/2024-3/7/2024 | Second Quarter
Date: Actual
Cost :Plan | [18 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xvii.Capacity building of Technical personals on solar based installation and maintenance | 020411/02 | STOWA/2024/16 | NA | 5 Million | 5Million | Direct method | 3/4/2024-5/4/2024 | 8/4/2023-12/4/2024 | NA | Direct | Direct | Direct | Direct | Direct | Direct | Direct | Direct | Direct | 26/6/2024-3/7/2024 | Second Quarter
Date: Actual
Cost :Plan | [7 empty] | 70000 |  |  | 50000 |  |  | 120000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xviii. Reconstruction of 4No. Zonal offices at Jahun, Dutse, Ringim and Kazaure | 020411/02 | STOWA/2024/CP/17 | NA | 50 million | 50 million | sellective method | 3/4/2024-5/4/2024 | 8/4/2023-12/4/2024 | NA | 12/04/2023-19/4/2024 | 19/4/2024-24/4/2024 | 25/4/2024-30/4/2024 | 1/5/2024-6/5/2024 | 6/5/2024-15/5/2024 | 15/5/2024-22/5/2024 | 22/5/2024-29/5/2024 | 29/6/2024-5/6/2024 | 5/6/2024-26/6/2024 | 26/6/2024-3/7/2024 | Second Quarter
Date: Actual
Cost :Plan | [7 empty] | 20000 |  |  | 30000 |  |  | 120000 | 30000 |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xix. Procurement of 1No. Toyota Hillux project vehicles and Toyota corolla(2014 model) | 020411/02 | STOWA/2024/PRCMNT/18 | NA | 60 million | 60million | Sellective method | 3/4/2024-5/4/2024 | 8/4/2023-12/4/2024 | NA | 12/04/2023-19/4/2024 | 19/4/2024-24/4/2024 | 25/4/2024-30/4/2024 | 1/5/2024-6/5/2024 | 6/5/2024-15/5/2024 | 15/5/2024-22/5/2024 | 22/5/2024-29/5/2024 | 29/6/2024-5/6/2024 | 5/6/2024-26/6/2024 | 26/6/2024-3/7/2024 | Second Quarter
Date: Actual
Cost :Plan | [7 empty] | 30000 |  |  | 50000 | [7 empty] | 30000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxi. Construction of public convenience at small towns | 020412/02 | STOWA/2024/CP/19 | NA | 10million | 10 million | Selective method | 3/4/2024-5/4/2024 | 8/4/2023-12/4/2024 | NA | 12/04/2023-19/4/2024 | 19/4/2024-24/4/2024 | 25/4/2024-30/4/2024 | 1/5/2024-6/5/2024 | 6/5/2024-15/5/2024 | 15/5/2024-22/5/2024 | 22/5/2024-29/5/2024 | 29/6/2024-5/6/2024 | 5/6/2024-26/6/2024 | 26/6/2024-3/7/2024 | Second Quarter
Date: Actual
Cost :Plan | [18 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxii. Community mobilization and sensitization on open defecation at small towns | 020412/02 | STOWA/2024/20 | NA | 20 million | 20 million | Direct method | 3/4/2024-5/4/2024 | 8/4/2023-12/4/2024 | NA | Direct | Direct | Direct | Direct | Direct | Direct | Direct | Direct | 5/6/2024-26/6/2024 | 26/6/2024-3/7/2024 | Second Quarter
Date: Actual
Cost :Plan | [7 empty] | Ongoing project | [10 empty] | 30000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxiii.Rehabilitation of existing small towns water supply schemes | 020404/02 | STOWA/2024/CP/21 | NA | 300 Million | 50 Million | selective competitive Method | 4/7/2024-7/7/2024 | 7/7/2024-14/7/2024 | NA | 14/7/2024-21/7/2024 | 21/7/2024-28/7/2024 | 28/7/2024-5/8/2024 | 5/8/2024-10/8/2024 | 10/8/2024-17/8/2024 | 17/8/2024-24/8/2024 | 24/8/2024-26/8/2024 | 26/8/2024-29/8/2024 | 29/8/2024-19/09/2024 | 19/09/2024-26/09/2024 | Third Quarter
Date: Actual
Cost :Plan | [7 empty] | 70000 |  |  | 50000 |  |  | 120000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxiv.Establishment of WCAs in community and several follow up visit to 200 communities for monitoring activities | 020411/02 | STOWA/2024/WCA/22 | NA | 10 million | 10 million | Direct | 4/7/2024-7/7/2024 | 7/7/2024-14/7/2024 | NA | Direct | Direct | Direct | Direct | Direct | Direct | 24/8/2024-26/8/2024 | Direct | Direct | 19/09/2024-26/09/2024 | Third Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Director Community Mobilization | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxv. Reconstruction of 4No. Zonal offices at Jahun, Dutse, Ringim and Kazaure | 020411/02 | STOWA/2024/CP/23 | NA | 50 million | 50 million | selective competitive Method | 4/7/2024-7/7/2024 | 7/7/2024-14/7/2024 | NA | 14/7/2024-21/7/2024 | 21/7/2024-28/7/2024 | 28/7/2024-5/8/2024 | 5/8/2024-10/8/2024 | 10/8/2024-17/8/2024 | 17/8/2024-24/8/2024 | 24/8/2024-26/8/2024 | 26/8/2024-29/8/2024 | 29/8/2024-19/09/2024 | 19/09/2024-26/09/2024 | Third Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Director Community Mobilization | [6 empty] | MD |  | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxvi. Community mobilization and sesitization on open Defication at small towns | 020412/02 | STOWA/2024/SENSITIZATION/24 | NA | 20 million | 20 million | Direct | 4/7/2024-7/7/2024 | 7/7/2024-14/7/2024 | NA | Direct | Direct | Direct | Direct | Direct | Direct | 24/8/2024-26/8/2024 | Direct | Direct | 19/09/2024-26/09/2024 | Third Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Director Community Mobilization | [6 empty] | MD |  | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxvii. Construction of public convenience at small towns | 020412/02 | STOWA/2024/CP/24 | NA | 10 million | 10 million | Nominative Method | 4/7/2024-7/7/2024 | 7/7/2024-14/7/2024 | NA | 14/7/2024-21/7/2024 | 21/7/2024-28/7/2024 | 28/7/2024-5/8/2024 | 5/8/2024-10/8/2024 | 10/8/2024-17/8/2024 | 17/8/2024-24/8/2024 | 24/8/2024-26/8/2024 | 26/8/2024-29/8/2024 | 29/8/2024-19/09/2024 | 19/09/2024-26/09/2024 | Third Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | [6 empty] | MD |  | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxviii. Reinforcement/inprovement of reticulation for 5 kilometer in small towns | 020406/02 | STOWA/2024/CP/25 | NA | 30 million | 10 million | Nominative Method | 4/7/2024-7/7/2024 | 7/7/2024-14/7/2024 | NA | 14/7/2024-21/7/2024 | 21/7/2024-28/7/2024 | 28/7/2024-5/8/2024 | 5/8/2024-10/8/2024 | 10/8/2024-17/8/2024 | 17/8/2024-24/8/2024 | 24/8/2024-26/8/2024 | 26/8/2024-29/8/2024 | 29/8/2024-19/09/2024 | 19/09/2024-26/09/2024 | Third Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | [6 empty] | MD |  | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxix. Drilling of 5No. Complete borehols with accessories | 020406/02 | STOWA/2024/CP/25 | NA | 10 million | 5 million | Nominative Method | 4/7/2024-7/7/2024 | 7/7/2024-14/7/2024 | NA | 14/7/2024-21/7/2024 | 21/7/2024-28/7/2024 | 28/7/2024-5/8/2024 | 5/8/2024-10/8/2024 | 10/8/2024-17/8/2024 | 17/8/2024-24/8/2024 | 24/8/2024-26/8/2024 | 26/8/2024-29/8/2024 | 29/8/2024-19/09/2024 | 19/09/2024-26/09/2024 | Third Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | [6 empty] | MD |  | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxix. Upgrading and conversion of 40No. Motorized water supply scheme to solar powered water supply scheme | 020408/02 | STOWA/2024/CP/26 | NA | 400 million | 100 million | Selective competetive Method | 4/7/2024-7/7/2024 | 7/7/2024-14/7/2024 | NA | 14/7/2024-21/7/2024 | 21/7/2024-28/7/2024 | 28/7/2024-5/8/2024 | 5/8/2024-10/8/2024 | 10/8/2024-17/8/2024 | 17/8/2024-24/8/2024 | 24/8/2024-26/8/2024 | 26/8/2024-29/8/2024 | 29/8/2024-19/09/2024 | 19/09/2024-26/09/2024 | Third Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | [6 empty] | MD |  | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxix. Construction of 30No. New solar powered schemes across the 7 zones | 020408/02 | STOWA/2024/CP/27 | NA | 300 million | 50 million | Selective competetive Method | 4/7/2024-7/7/2024 | 7/7/2024-14/7/2024 | NA | 14/7/2024-21/7/2024 | 21/7/2024-28/7/2024 | 28/7/2024-5/8/2024 | 5/8/2024-10/8/2024 | 10/8/2024-17/8/2024 | 17/8/2024-24/8/2024 | 24/8/2024-26/8/2024 | 26/8/2024-29/8/2024 | 29/8/2024-19/09/2024 | 19/09/2024-26/09/2024 | Third Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | [6 empty] | MD |  | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxix. Completion of 2022/2023 constituency projects | 020408/02 | STOWA/2024/CP/27 | NA | 216 million | 50 million | Open competetive Method | Ongoing project | Ongoing project | NA | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | 29/8/2024-19/09/2024 | 19/09/2024-26/09/2024 | Third Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | [6 empty] | MD |  | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxix. Commencement of 2024 constituency | 020408/02 | STOWA/2024/CP/28 | NA | 211.9million | 211.9 million | Open competetive Method | 4/7/2024-7/7/2024 | 7/7/2024-14/7/2024 | NA | 14/7/2024-21/7/2024 | 21/7/2024-29/7/2024 | 29/7/2024-9/09/2024 | 9/09/2024-16/09/2024 | 16/09/2024-18/09/2024 | 18/09/2024-19/09/2024 | 19/09/2024-26/09/2024 | 26/09/2024-30/09/2024 | 30/09/2024-01/10/2024 | 01/10/2024-08/10/2024 | Third Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | [6 empty] | MD |  | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxix. Completion of 2022/2023 constituency projects | 020408/02 | STOWA/2024/CP/29 | NA | 216 million | 16 million | Open competetive Method | Ongoing project | Ongoing project | NA | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | 20/12/2024-23/12/2024 | 23/12/2024-27/12/2024 | Forth Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | [6 empty] | MD |  | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxix. Commencement of 2024 constituency | 020408/02 | STOWA/2024/CP/30 | NA | 211.9million | 211.9 million | Open competetive Method | 27/09/2024-30/09/2024 | 30/09/2024-4/10/2024 | NA | 4/10/2024-11/10/2024 | 11/10/2024-14/10/2024 | 14/10/2024-25/10/2024 | 25/11/2024-02/12/2024 | 02/12/2024-09/12/2024 | 09/12/2024-16/12/2024 | 16/12/2024-17/12/2024 | 17/12/2024-20/12/2024 | 20/12/2024-23/10/2024 | 23/12/2024-27/12/2024 | Forth Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | [6 empty] | MD |  | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxiv.Establishment of WCAs in community and several follow up visit to 200 communities for monitoring activities | 020411/02 | STOWA/2024/WCA/31 | NA | 10 million | 10 million | Direct | 30/09/2024-7/10/2024 | 7/10/2024-14/10/2024 | NA | Direct | Direct | Direct | Direct | Direct | Direct | 20/11/2024-27/8/2024 | Direct | Direct | 17/12/2024-24/12/2024 | Forth Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Director Community Mobilization | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance

## CS
PROCUREMENT PLAN FOR CONSULTING SERVICES.
MINISTRY/ AGENCY:
BUDGET YEAR:
Project Description | Package Number | CONTRACT TYPE |  |  |  | PREPARATION OF PROPOSALS |  |  |  | SHORTLIST |  | CONSULTANT PROPOSAL |  | PROPOSAL EVALUATION AND NEGOTIATION | [5 empty] | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
|  | Lumpsum or Time-Based | Budgetary Amount in Naira | Plan Vs Actual | Approval Threshhold | Preparation and Submission by MDAs | MDA Approval/ LASPPA 'Certificate of Compliance" | Advertisement | Lead-Time Beforte Shortlist | Submission Date | MDA Approval/ LASPPA 'Certificate of Compliance" | Invitation Date | Submission / Opening Date | Submission Evaluation Report (T) | MDA Approval/ LASPPA 'Certificate of Compliance" | Opening/ Evaluation of Financial Proposals | Submission Evaluation Report (T) (F) | Negotiation (if any) | Certificate of Clearance Date | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion